## User Stories
ID | Module | Title | As a/an | I want to… | so that I can… | Itertions | Story Points | Story Constraints
1.1 | Customer Account | Register | Customer | Register to the website | Register to the website and Log in to access the features. | Last Semester |  | Customer should see an option to Register/Sign-up and login screen with input data fields for 1) Username 2) Password
1.2 | Customer Account | Sign in Account | Customer | Login to the website | Log in to the website, Access the application and use the provided features | Last Semester |  | Existing Customer can login with input data fields for 1) Username 2) Password and access the the website.
1.3 | Customer Account | Contact Tech Support | Customer | Resolve technical issues | Contact support for the issues to be resolved. | I2 | 6 | Customer contacts to the tech support team with an issue of accessing the website for troubleshooting.
1.4 | Customer Account | Pay For Service | Customer | Select my desired services | Book and reserve desired activity | I2 | 9 | A registered customer can see the various services and pay for the services to use them.
1.5 | Customer Account | Update Account | Customer | Updating the profile | Update my account so that I can have up to date information in my account and be able to delete it when I no longer need it. | I1 | 3 | The customer can update his personal information (ex. contact info) and update his account.
1.6 | Customer Account | delete Account | Customer | delete the account | Delete the account as I am no longer using it | I1 | 3 | The customer has an option to remove all his information and delete his account permanently.
1.7 | Customer Account | View Booking History | Customer | Selected activity | Verify the booking schedule if the user forgets to add some services | I1 | 6 | Customers can easily check if the booking has been made by themselves - as well as the whole history of the booking.
1.8 | Customer Account | Rate Musicians | Customer | Rate the musicians whose service I have used | Rate the musicians based on service provided so that it can be helpful for the other customers when they visit the application |  |  | A customer has the option to rate the musician whose services they used or the musician they know.
2.1 | Musician Account | Register Account | Subscribed Musicians | Register to the website | Create an account to login. |  |  | Musician should see an option to Register and login screen with input data fields for 1) Username 2) Password.
2.2 | Musician Account | Add Services | Subscribed Musicians | Enter the kind of service I provide | Display the services which I provide to customers. | i3 | 9 | A musician can add their services and describe them so that customers can buy easily.
2.3 | Musician Account | View Booking history | Subscribed Musicians | Check my booking history | Check the type of service that customer chose. | I1 | 3 | Musician can easily check if they have any bookings as well as the whole history of the booking.
2.4 | Musician Account | Sign-in for Account | Subscribed Musicians | Enter the website | Login in to the website to use the services. |  |  | Musician should see an option to Sign-up and login screen with input data fields for 1) Username 2) Password
2.5 | Musician Account | Define Payment Method | Subscribed Musicians | Have option to make payment | Make a payment for the services chosen. |  | - | A registerd musician can put the various payment methods for their services so that customers can buy.
2.6 | Musician Account | Update Account info | Subscribed Musicians | Update my account details | Update personel information like phone number, address, email etc. | I1 | 3 | The customer can update his personal information (ex. contact info) and update his account.
2.7 | Musician Account | Close Account | Subscribed Musicians | Delete my account | Delete account if I feel it is no longer necessary. | I1 | 3 | The musician has an option to remove all his services and delete his account permanently.
2.8 | Musician Account | Rate Customer | Subscribed Musicians | Rate the customer who chose a musician service | Rating the customers which helps other musicians to confirm their booking or not |  |  | A musician has the option to rate the genuine cutomer.
3.1 | Admin module | Manage Admin Users | It Support, Lead Engineer, Sr Manager | Manage Admin users | Add/modify/delete Admin and their rights. |  | 6 | Give the rights for admin account and can add/delete or modified the persons in admin pannel.
3.2 | Admin module | Manage Customer | It Support | Manage the Customers registered on the system. | Add/modify/delete any Customer. |  | 9 | An admin can manage all registered customer's accounts and delete or modified if any problems will be occurring.
3.3 | Admin module | Manage Musicians | It Support | Manage the Musicians/Bands registered on the system. | Review/approve/reject/modify any Musician's account. |  | 9 | An admin can manage all registered musician's accounts and delete or modified if any problems will be occurring.
3.4 | Admin module | Decline/Cancelled Bookings for Customers and Musicians | It Support | Manage customer/musician booking account | See the booking information of every individual Customers/musicians. |  | 6 | An admin has the right to declined/cancelled the service if anythings is wrong.
3.5 | Admin module | Generate performance reports | It Support, Lead Engineer, Sr Manager | See various reports | Keep record of Payment Reports, Invoices, total Earning Report, Musician Payment/Earning Reports. |  | 3 | Admin can generate the performance report of the website after analyzing all data.
3.6 | Admin module | Manage Location Services | Lead Engineer, Sr Manager | Manage locations into which web application will offer its services | Can add/modify/delete location(s). |  | 9 | None
3.7 | Admin module | Manage Manual Booking | It Support | Manage booking for customers | Do bookings for those who have trouble accessing the web application. |  | 3 | If any customer has an issue in booking then they can contact admin and admin will manage that customer's booking.
3.8 | Admin module | Booking Management | It Support | See booking history | Filter the booking by Date, Musician, Customer and view invoice for any Booking. |  | 3 | Admin has a right to view all customers and musicians' booking history to make an invoice.
3.9 | Admin module | Manage Music Genere | Lead Engineer, Sr Manager | Manage the Music Genre/Categories shown in the web application. | Define the Music Genre name and other details. |  | 3 | Admin will add the filter process in musician's service like music genre and music catgories so that it's easy for customer to choose musician.
3.1 | Admin module | Generating Promo Code | It Support | Generate promo codes | Provide discount and offers to customers and promote services. |  | 3 | Admin has a right to view all customers and musicians' booking history to make an invoice.
3.11 | Admin module | Manage Commision Charges | It Support | Manage price rate for customers and musician | Define the Commision(%) charges for musicians, Cancellation Charges for customers. |  | 3 | Admin has to manage prices criteria for the musician's service and manage commission charges for musicians and cancellation of customer's booking.
3.12 | Admin module | Manage Reviews | Lead Engineer | See all reviews | See feedbacks that have been given over the web application by Customer for the Musicians as well as for the Customers by the Musicians. |  | 6 | Admin can manage all reviews/ratings and feedbacks given by the customers and muscians over the web appliction. Also he can add/delete/modify any reviews/feedbacks.
3.13 | Admin module | Manage Advertisement | Lead Engineer | Promote, highlight or even showcase the different offers/advertisements as well as information about the web application | Reflect those details/information on the Home page of the application. |  | 6 | Admin can put some attractive advertisement like (ex. discount offers, some musical events, etc) on the web application's homepage for more business advantages.
3.14 | Admin module | Manage Helpdesk Tickets | Lead Engineer |  |  |  | 3 | None
4.1 | Booking | Generate Customer Booking summary | It Support | See Booking summary | Check all the information related to bookings. | I2 | 6 | check if the customer had made any bookings of musicians or related events in the past month then a summaray is generated based on that data else no summary is shown to the customer
4.2 | Booking | Generate Musician Booking Summary | It Support | See Booking summary | Check all the information related to bookings. | I2 | 6 | Check if a musician have been reserved for an event in the past month or so then a summary is generated based on that data else no summary is shown to the musician
4.3 | Booking | Browse past, current, and future Booking Records | Subscribed Musicians | See Booking summary | Check all the information about past bookings. | I2 | 3 | Musician has to make sure that he done the authentication properly so that he can access his past bookings.
4.4 | Booking | Search Musicians by geographic location, genre, and date to finalize reservation/booking | Subscribed Musicians | Search the artists and services by location, music genre, date, and time. | Easliy find best matched artist. |  | 9 | None
4.5 | Booking | Process Payment and Generate Invoices | Accountant | Handle the payment | Accept payments from customers, payout the commision to the musicians, and generate invoices for both parites. |  |  | The Accountant has to make sure that all the fields are filled completely while processing a payment so that invoices are generated simultaneously.
4.6 | Booking | Search Musicians by geographic location, genre, and date to finalize reservation/booking | It Support | Search the artists and services by location, music genre, date, and time. | Based on the location of Musincians and their available dates finalize booking. |  |  | None
4.7 | Booking | Generating financial reports | It Support, Accountant | Generate financial reports for internal purpose. | Record all the information related to payments. |  |  | It support personel must have access to the data of the accountant to generate financilal records of the total payments made.
5.1 | Advertisement | Post Advertisements | Subscribed Musicians, Ad representative | Post a new advertisement | Upload advertisement to the website. |  |  | The Ad representative must verify the contents of the advertisement before posting on the website
5.2 | Advertisement | Post History and Statistical Data | Ad representative, Market representative | Check advertisements post history | Click on the button to view old advertisement. |  |  | None
5.3 | Advertisement | Post Modification | Ad representative, Market representative | Make changes in the advertisement | Upload changed advertisement to the web server . |  |  | Before making changes to the previous advertisement the representatice must make sure it doesn't affect the webpage structure.
6.1 | Customer Support/ Feedback | Create and monitor customer service tickets | CS Manager, It support | Monitor customer service tickets | Click on the button to view all the service tickets. |  | 6 | None
6.2 | Customer Support/ Feedback | Escalate Customer Support Tickets | CS Manager, It support | Update customer support ticket | Upload new status of support ticket to the server. |  | 3 | Customer support personel should be available 24x7 to update the status of ticket whenever a ticket is resolved/
6.3 | Customer Support/ Feedback | Resolve Customer Support Tickets | CS Manager | Help users solve queries | Clear the queries of customers and reflect the changes in their account. |  | 6 | Should be available 24 hour to troubleshoot an issue and provide information about sytem and services.
6.4 | Customer Support/ Feedback | Communicate with end user | CS Manager, It support | Contact with end users | Confirm resolution of end users complaints. |  | 3 | Before contacting the end user the IT support must confirm the status of the ticket to be completed.
6.5 | Customer Support/ Feedback | Access accounts and payment information of customers and musicians | CS Manager, It support | Check payment detail | Confirm check purchase history and information. |  | 3 | None
6.6 | Customer Support/ Feedback | Freeze and unfreeze Accounts | CS Manager, It support | Freeze user accounts | Remove accounts in case of breach of terms of service. |  | 6 | None