## Road Map
UnitedTune
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/15/21 | Iteration 2 - 11/05/21 | Iteration 3 - 11/19/21 | Iteration 4 - 12/17/21
01.Customer Account | 1.1 Register
1.2 Sign In Account
| 1.3 Contact Tech Support | 6 |  | X
| 1.4 Pay For Service | 9 |  | X
| 1.5 Update Account | 5 | X
| 1.6 Delete Account | 3 | X
| 1.7 View Booking History | 3 | X
1.8 Rate Musicians
02. Musician Account | 2.01 Register Account
| 2.02 Add Services | 9 |  |  | X
| 2.03 View Booking history | 3 | X
2.04 Sign-in for Account
2.05 Define Payment Method
| 2.06 Update Account info | 5 | X
| 2.07 Close Account | 3 | X
2.08 Rate Customers
03. Admin module | 03.01 Manage Admin Users
| 03.02 Manage Customers | 9 |  |  | X
03.03 Musicians Management
03.04 Decline/Cancelled Bookings for Customers and Musicians
| 03.05 Generate Reports | 3 |  |  | X
03.06 Manage Location Services
| 03.07 Manage Manual Booking | 3 |  |  | X
| 03.08 Manage Booking | 3 |  |  | X
| 03.09 Manage Music Genre | 3 |  |  | X
| 03.10 Generate Promo Code | 3 |  |  | X
| 03.11 Manage Commission and Charges | 3 |  |  | X
03.12 Manage Reviews
03.13 Manage Advertisement
| 03.14 Manage Helpdesk Tickets | 3 |  |  | X
04. Booking | 04.01 Generate Customer Booking summary | 8 |  | X
| 04.02 Generate Musician Booking Summary | 8 |  | X
| 04.03 Browse past, current, and future Booking Records | 5 |  | X
04.04 Search Musicians by geographic location, genre, and date to finalize reservation/booking
04.05 Provide quotes on requested services
04.06 Process Payment and Generate Invoices
04.07 Generate financial reports
05. Advertiement | 05.01 Post Advertisements
05.02 Post History and Statistical Data
05.03 Post Modification
06. Customer Service | 06.01 Create and monitor customer service tickets | 6 |  |  |  | X
| 06.02 Handle Financial Disputes | 3 |  |  |  | X
| 06.03 Resolve Customer Support Tickets | 6 |  |  |  | X
| 06.04 Communicate with the end user | 3 |  |  |  | X
| 06.05 Access customer account information | 3 |  |  |  | X
| 06.06 Freeze and unfreeze Accounts | 6 |  |  |  | X
|  | VELOCITY: | 22 | 36 | 39 | 27

## Story Map
Epics |  | UnitedTune - User Story Map
Epic 1 - Customer Account |  | Epic 1 - Customer Account | Epic 2 - Musician Account | Epic 3 - Admin module | Epic 4 - Booking | Epic 5 - Advertiement | Epic 6 - Customer Service
Epic 2 - Musician Account | User Stories | 1.5 Update Account | 2.03 View Booking history
Epic 3 - Admin module |  | 1.6 Delete Account | 2.06 Update Account info
Epic 4 - Booking |  | 1.7 View Booking History | 2.07 Close Account
Epic 5 - Advertiement | [7 empty] | Iteration 1
Epic 6 - Customer Service |  | 1.3 Contact Tech Support |  |  | 04.01 Generate Customer Booking summary
|  | 1.4 Pay For Service |  |  | 04.02 Generate Musician Booking Summary
[5 empty] | 04.03 Browse past, current, and future Booking Records |  |  | Iteration 2
|  |  | 2.02 Add Services | 03.02 Manage Customers
03.05 Generate Reports
03.07 Manage Manual Booking
03.08 Manage Booking
03.09 Manage Music Genre
03.10 Generate Promo Code
03.11 Manage Commission and Charges
|  |  |  | 03.14 Manage Helpdesk Tickets |  |  |  | Iteration 3
06.01 Create and monitor customer service tickets
06.02 Handle Financial Disputes
06.03 Resolve Customer Support Tickets
06.04 Communicate with the end user
06.05 Access customer account information
[7 empty] | 06.06 Freeze and unfreeze Accounts | Iteration 4