## Project Plan for UnitedTune
RAG Status Key | Not completed |  |  |  | SPRING 2021
In Progress
| Completed |  |  |  | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2021-01-26 | 2021-02-02 | 2021-02-09 | 2021-02-16 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-13 | 2021-04-20 | 2021-04-27 | 2018-05-04
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Brainstorm project ideas and select two project proposals | ALL | 2021-01-26 | 2021-02-01 | 100%
| Develop two business cases | John Brilhart | 2021-01-26 | 2021-02-01 | 100%
| Create initial Project Initiation Document (PID) | John Brilhart | 2021-02-02 | 2021-02-08 | 100%
| Produce initial Project Plan, RACI | John Brilhart | 2021-02-09 | 2021-02-15 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Create BRM Diagram, User Roles | Jay Patel | 2021-02-16 | 2021-02-22 | 100%
| Produce Context Diagram, System Interface Table | Yashwanth Varre, Ge Ou | 2021-02-16 | 2021-02-22 | 100%
| Confirm Requirements Types, and update the tasks in Project Plan | Yashwanth Varre, Ge Ou | 2021-02-16 | 2021-02-22 | 100%
| Discuss and decide business requierments | Jay Patel | 2021-02-23 | 2021-03-01 | 100%
| Create Functional Decomposition | Yashwanth Varre | 2021-02-23 | 2021-03-01 | 100%
| Create Fishbone Diagram | Ge Ou | 2021-02-23 | 2021-03-01 | 100%
| Brainstorm features to develop on web application | All | 2021-02-09 | 2021-02-15 | 100%
| Complete BRD(Stakeholder requierments) | Jay Patel | 2021-02-23 | 2021-03-01 | 100%
| Design RCT (includes supplementary reqs) | Yashwanth Varre | 2021-03-02 | 2021-03-08 | 100%
| Create User Stories | Ge Ou | 2021-03-02 | 2021-03-08 | 100%
| Create Data Flow Diagram | Yashwanth Varre | 2021-03-02 | 2021-03-08 | 100%
| Produce UML analysis Diagrams | Ge Ou | 2021-03-02 | 2021-03-08 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Design Home Page menu structure | Hetali Chavda | 2021-02-23 | 2021-03-01 | 100%
| Initial design of Home Page | Hetali Chavda | 2021-02-09 | 2021-02-15 | 100%
| Produce ER Diagrams (conceptual, logical) | Revati Deshmukh | 2021-03-30 | 2021-04-05 | 0%
| Produce Database Table Specs(Data dictionary) | Revati Deshmukh | 2021-03-30 | 2021-04-05 | 0%
| Create Data-flow Diagram (physical) | Yashwanth Varre, Ge Ou | 2021-03-30 | 2021-04-05 | 0%
| Create Architecture Diagrams (2) | Revati Deshmukh, Hetali Chavda | 2021-04-06 | 2021-04-12 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | Code Customer Portal | Hetali Chavda | 2021-03-30 | 2021-04-05 | 0%
| Finish coding Home Page | Hetali Chavda | 2021-04-06 | 2021-04-12 | 0%
| Create Class Diagram | Hetali Chavda | 2021-04-13 | 2021-04-19 | 0%
| Create Sequence Diagram | Hetali Chavda | 2021-04-13 | 2021-04-19 | 0%
| Create Musician Portal | Hetali Chavda | 2021-04-13 | 2021-04-19 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Make Test Plan document | Hetali Chavda | 2021-04-20 | 2021-04-26 | 0%
| Test execution | Suraj Suwal | 2021-04-27 | 2021-05-03 | 0%
| Design Test Cases for Customer Portal | Suraj Suwal | 2021-04-20 | 2021-04-26 | 0%
| Design Test Cases for Musician Portal | Suraj Suwal | 2021-04-20 | 2021-04-26 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2021-05-04 | 2021-05-10 | 0%