## Road Map
UnitedTune
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/15/21 | Iteration 2 - 11/05/21 | Iteration 3 - 11/19/21 | Iteration 4 - 12/17/21
01.Customer Account | 1.1 Register
1.2 Sign In Account
| 1.3 Contact Tech Support | 6 |  | X
| 1.4 Pay For Service | 9 |  | X
| 1.5 Update Account | 3 | X
| 1.6 Delete Account | 3 | X
| 1.7 View Booking History | 6 | X
1.8 Rate Musicians
02. Musician Account | 2.01 Register Account
| 2.02 Add Services | 9 | X
| 2.03 View Booking history | 3 | X
2.04 Sign-in for Account
2.05 Define Payment Method
| 2.06 Update Account info | 3 | X
| 2.07 Close Account | 3 | X
2.08 Rate Customers
03. Admin module | 03.01 Manage Admin Users | 6 |  |  | X
| 03.02 Manage Customers | 9 |  |  | X
| 03.03 Musicians Management | 9 |  |  | X
| 03.04 Decline/Cancelled Bookings for Customers and Musicians | 6 |  |  | X
| 03.05 Generate Reports | 3 |  |  | X
| 03.06 Manage Location Services | 9 |  |  | X
| 03.07 Manage Manual Booking | 3 |  |  | X
| 03.08 Manage Booking | 3 |  |  | X
| 03.09 Manage Music Genre | 3 |  |  | X
| 03.10 Generate Promo Code | 3 |  |  | X
| 03.11 Manage Commission and Charges | 3 |  |  | X
| 03.12 Manage Reviews | 6 |  |  | X
| 03.13 Manage Advertisement | 6 |  |  | X
| 03.14 Manage Helpdesk Tickets | 3 |  |  | X
04. Booking | 04.01 Generate Customer Booking summary | 6 |  | X
| 04.02 Generate Musician Booking Summary | 6 |  | X
| 04.03 Browse past, current, and future Booking Records | 3 |  | X
| 04.04 Search Musicians by geographic location, genre, and date to finalize reservation/booking | 9 |  | X
04.05 Provide quotes on requested services
04.06 Process Payment and Generate Invoices
04.07 Generate financial reports
05. Advertiement | 05.01 Post Advertisements
05.02 Post History and Statistical Data
05.03 Post Modification
06. Customer Service | 06.01 Create and monitor customer service tickets | 6 |  |  |  | X
| 06.02 Handle Financial Disputes | 3 |  |  |  | X
| 06.03 Resolve Customer Support Tickets | 6 |  |  |  | X
| 06.04 Communicate with the end user | 3 |  |  |  | X
| 06.05 Access customer account information | 3 |  |  |  | X
| 06.06 Freeze and unfreeze Accounts | 6 |  |  |  | X
|  | VELOCITY: | 30 | 39 | 72 | 27

## Story Map
Epics |  | UnitedTune - User Story Map
Epic 1 - Customer Account |  | Epic 1 - Customer Account | Epic 2 - Musician Account | Epic 3 - Admin module | Epic 4 - Booking | Epic 5 - Advertiement | Epic 6 - Customer Service
Epic 2 - Musician Account | User Stories | 1.5 Update Account | 2.02 Add Services
Epic 3 - Admin module |  | 1.6 Delete Account | 2.03 View Booking history
Epic 4 - Booking |  | 1.7 View Booking History | 2.06 Update Account info
Epic 5 - Advertiement |  |  | 2.07 Close Account |  |  |  |  | Iteration 1
Epic 6 - Customer Service |  | 1.3 Contact Tech Support |  |  | 04.01 Generate Customer Booking summary
|  | 1.4 Pay For Service |  |  | 04.02 Generate Musician Booking Summary
04.03 Browse past, current, and future Booking Records
[5 empty] | 04.04 Search Musicians by geographic location, genre, and date to finalize reservation/booking |  |  | Iteration 2
03.01 Manage Admin Users
03.02 Manage Customers
03.03 Musicians Management
03.04 Decline/Cancelled Bookings for Customers and Musicians
03.05 Generate Reports
03.06 Manage Location Services
03.07 Manage Manual Booking
03.08 Manage Booking
03.09 Manage Music Genre
03.10 Generate Promo Code
03.11 Manage Commission and Charges
03.12 Manage Reviews
03.13 Manage Advertisement
|  |  |  | 03.14 Manage Helpdesk Tickets |  |  |  | Iteration 3
06.01 Create and monitor customer service tickets
06.02 Handle Financial Disputes
06.03 Resolve Customer Support Tickets
06.04 Communicate with the end user
06.05 Access customer account information
[7 empty] | 06.06 Freeze and unfreeze Accounts | Iteration 4