## R1 I1
Task# | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I1 | 01.Customer Account | 1.05 | Update Account | Implement GUI to allow customer to modify account details by adding appropriate fields and navigation | 2021-10-01 | 2021-10-03 | 100% | Revati Deshmukh
2 | R1 - I1 | 01.Customer Account | 1.05 | Update Account | Implement field validation to validate entries in fields to modify account details | 2021-10-01 | 2021-10-03 | 100% | Revati Deshmukh
3 | R1 - I1 | 01.Customer Account | 1.05 | Update Account | Implement core functionality of feature | 2021-10-01 | 2021-10-03 | 100% | Revati Deshmukh
4 | R1 - I1 | 01.Customer Account | 1.05 | Update Account | Design test cases for implemented crosscuts | 2021-10-01 | 2021-10-08 | 100% | Suraj Suwal, Soyeon Ju
5 | R1 - I1 | 01.Customer Account | 1.05 | Update Account | Execute test cases for implemented crosscuts | 2021-10-05 | 2021-10-08 | 100% | Suraj Suwal, Soyeon Ju
6 | R1 - I1 | 02. Musician Account | 2.06 | Update Account Info | Implement GUI to allow musician to modify account details by adding appropriate fields and navigation | 2021-10-03 | 2021-10-07 | 100% | Revati Deshmukh
7 | R1 - I1 | 02. Musician Account | 2.06 | Update Account Info | Implement field validation to validate entries in fields to modify musician account details | 2021-10-03 | 2021-10-07 | 100% | Revati Deshmukh
8 | R1 - I1 | 02. Musician Account | 2.06 | Update Account Info | Implement core functionality of feature | 2021-10-03 | 2021-10-07 | 100% | Revati Deshmukh
9 | R1 - I1 | 02. Musician Account | 2.06 | Update Account Info | Design test cases for implemented crosscuts | 2021-10-01 | 2021-10-08 | 100% | Suraj Suwal, Soyeon Ju
10 | R1 - I1 | 02. Musician Account | 2.06 | Update Account Info | Execute test cases for implemented crosscuts | 2021-10-05 | 2021-10-08 | 100% | Suraj Suwal, Soyeon Ju
11 | R1 - I1 | 01.Customer Account | 1.06 | Delete Account | Implement GUI | 2021-10-07 | 2021-10-09 | 100% | Revati Deshmukh
12 | R1 - I1 | 01.Customer Account | 1.06 | Delete Account | Implement core functionality of feature | 2021-10-07 | 2021-10-09 | 100% | Revati Deshmukh
13 | R1 - I1 | 01.Customer Account | 1.06 | Delete Account | Design test cases for implemented crosscuts | 2021-10-01 | 2021-10-08 | 100% | Suraj Suwal, Soyeon Ju
14 | R1 - I1 | 01.Customer Account | 1.06 | Delete Account | Execute test cases for implemented crosscuts | 2021-10-07 | 2021-10-09 | 100% | Suraj Suwal, Soyeon Ju
15 | R1 - I1 | 02. Musician Account | 2.07 | Close Account | Implement GUI | 2021-10-08 | 2021-10-11 | 100% | Revati Deshmukh
16 | R1 - I1 | 02. Musician Account | 2.07 | Close Account | Implement core functionality of feature | 2021-10-08 | 2021-10-11 | 100% | Revati Deshmukh
17 | R1 - I1 | 02. Musician Account | 2.07 | Close Account | Design test cases for implemented crosscuts | 2021-10-01 | 2021-10-08 | 100% | Suraj Suwal, Soyeon Ju
18 | R1 - I1 | 02. Musician Account | 2.07 | Close Account | Execute test cases for implemented crosscuts | 2021-10-08 | 2021-10-11 | 100% | Suraj Suwal, Soyeon Ju
19 | R1 - I1 | 01.Customer Account | 1.07 | View Booking history | Implement GUI | 2021-10-11 | 2021-10-13 | 100% | Revati Deshmukh
20 | R1 - I1 | 01.Customer Account | 1.07 | View Booking history | Implement Entitlements for the role of Customer | 2021-10-11 | 2021-10-13 | 100% | Revati Deshmukh
21 | R1 - I1 | 01.Customer Account | 1.07 | View Booking history | Implement System Interface | 2021-10-11 | 2021-10-13 | 100% | Revati Deshmukh
22 | R1 - I1 | 01.Customer Account | 1.07 | View Booking history | Implement core functionality of feature | 2021-10-11 | 10/113/2021 | 100% | Revati Deshmukh
23 | R1 - I1 | 01.Customer Account | 1.07 | View Booking history | Design test cases for implemented crosscuts | 2021-10-01 | 2021-10-08 | 100% | Suraj Suwal, Soyeon Ju
24 | R1 - I1 | 01.Customer Account | 1.07 | View Booking history | Execute test cases for implemented crosscuts | 2021-10-11 | 2021-10-13 | 100% | Suraj Suwal, Soyeon Ju
25 | R1 - I1 | 02. Musician Account | 2.03 | View Booking history | Implement GUI | 2021-10-13 | 2021-10-15 | 100% | Revati Deshmukh
26 | R1 - I1 | 02. Musician Account | 2.03 | View Booking history | Implement Entitlements for the role of Musician | 2021-10-13 | 2021-10-15 | 100% | Revati Deshmukh
27 | R1 - I1 | 02. Musician Account | 2.03 | View Booking history | Implement System Interface | 2021-10-13 | 2021-10-15 | 100% | Revati Deshmukh
28 | R1 - I1 | 02. Musician Account | 2.03 | View Booking history | Implement core functionality of feature | 2021-10-13 | 2021-10-15 | 100% | Revati Deshmukh
29 | R1- l1 | 02. Musician Account | 2.03 | View Booking history | Design test cases for implemented crosscuts | 2021-10-01 | 2021-10-08 | 100% | Suraj Suwal, Soyeon Ju
30 | R1- l1 | 02. Musician Account | 2.03 | View Booking history | Execute test cases for implemented crosscuts | 2021-10-13 | 2021-10-15 | 100% | Suraj Suwal, Soyeon Ju