## RACI
Team 2 RACI Document |  | Project Roles
Project Phase | Project Tasks | Project Manager | Product Owner | Dev Lead | BA Lead | Business Analyst | Tester | DBA | QA Analyst
Project Management | Organizing Weekly Meeting | A,R | C | C | C | C | C | C | C
| Create and maintain a shared google drive folder | A,R | C | C | C | C | C | C | C
| Delegate tasks | A,R | I | C | I | I | I | I | I
| Create Project Plan | A,R | I | I | I | I | I | I | I
| Update project status on project plan | A,R | I | I | I | I | I | I | I
Requirements | Create requirements analysts | A | C | C | R | R | C | C | C
| Gather business requirements | A | C | C | R | R | C | C | C
| Produce functional requirements | A | C | C | R | R | I | I | I
Design | Produce high-level design specs | A | I | R | I | C | I | C | C
| Produce data model | A | I | R | I | C | I | R | R
| Create Database diagrams | A | I | I | I | I | I | R | I
| Produce detailed design specs | A | I | R | I | C | I | C | C
Coding | Establish a code repository (GitHub) | A | I | R | I | I | C | C | C
| Develop component code | A | I | R | I | I | I | C | I
Testing | Develop a test plan | A | I | C | I | I | R | C | C
| Establish a test repository | A | I | C | I | I | R | C | C
| Develop test specifications | A | I | C | I | I | R | C | C
| Execute testing, report defects | A | I | C | I | I | R | C | C
| Conduct defect review calls | A | I | C | I | I | R | C | C
| Produce, deliver defect metrics | A | I | C | I | I | R | C | C
| Support test environments | A | I | C | I | I | R | C | C
Deployment | Produce a deployment plan | A | I | R | I | I | I | R | R
| Produce deployment procedures | A | I | R | I | I | I | R | R
| Deploy software into production | A | I | R | I | I | I | R | R